## Sheet1
Backlog:	Initial Assessment:	Priority:	To Do By	Week One	Week Two
Start project backlog	3	High
Sprint 1:	3
Walking Skeleton	5	High	Nicholas	DONE	Done
Organize database fields	3	High	Everyone	50.00%
Personal List Database	3	High	Nicholas	DONE	Done
Start HTML Design	3	Medium	Lee	0	Done
Sprint 2:	14
Calendar Object design	8	High	Bill
HTML Template for Text Windows	3	Medium	Lee
Display Personal List	2	High	Nicholas		Done
Insert Email Reminder	5	Medium		Pushed to Later
Sprint 3:	18
Calendar Object, / Implemented for All uses	5	High
Administrator Tools	8	High
Member Sign in	5	High	Nicholas	Pushed Up
HTML content editable / Through Website	3	Medium
Sprint 4	21
Priority Membership	5	High
Administrator Tools Cont.	5	Medium
Fix existing Features	5	Medium
Add Events to Standby Calendar	3
Sprint 5:	18
Certifications Available	5	Low
Fix existing Features	5	Medium
Finished Program:	5