## Sheet1
Backlog:	Initial Assessment:	Priority:
Start project backlog	3	High
Sprint 1:	3
Walking Skeleton	5	High
Organize database fields	3	High
Personal List Database	3	High
Start HTML Design	3	Medium
Sprint 2:	14
Calendar Object design	8	High
HTML Template for Text Windows	3	Medium
Display Personal List	2	High
Insert Email Reminder	5	Medium
Sprint 3:	18
Calendar Object, / Implemented for All uses	5	High
Administrator Tools	8	High
Member Sign in	5	High
HTML content editable / Through Website	3	Medium
Sprint 4	21
Priority Membership	5	High
Administrator Tools Cont.	5	Medium
Fix existing Features	5	Medium
Add Events to Standby Calendar	3
Sprint 5:	18
Certifications Available	5	Low
Fix existing Features	5	Medium
Finished Program:	5