## Sheet1
Backlog:	Initial Assessment:	Priority:	To Do By	Week One	Week Two	Week Five
Start project backlog	3	High
Sprint 1:	3
Walking Skeleton	5	High	Nicholas	DONE	Done	Done
Organize database fields	3	High	Everyone	50.00%	80.00%	Done
Personal List Database	3	High	Nicholas	DONE	Done	Done
Start HTML Design	3	Medium	Lee	0	Done	Done
Sprint 2:	14
Calendar Object design	8	High	Bill		50.00%	Done
HTML Template for Text Windows	3	Medium	Lee		Done	Done
Display Personal List	2	High	Nicholas		Done	Done
Insert Email Reminder	5	Medium		Pushed to Later		25.00%
Sprint 3:	18
Calendar Object, / Implemented for All uses	5	High				50.00%
Administrator Tools	8	High				75.00%
Member Sign in	5	High	Nicholas	Pushed Up	75.00%	Done
HTML content editable / Through Website	3	Medium				Done
Sprint 4	21
Priority Membership	5	High				Done
Administrator Tools Cont.	5	Medium				75.00%
Fix existing Features	5	Medium				25.00%
Add Events to Standby Calendar	3
Sprint 5:	18
Certifications Available	5	Low
Fix existing Features	5	Medium
Finished Program:	10
Donuts	3	Highest